## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/05/23-09/12/23 | 1. Determined project, plan, roles 2. Made sure everyone understood the assignments and to-dos 3. The team had an initial understanding of what tools and processes the members need to learn 4. Wrote initial requirements 5. Wrote risk management plan |  | Hao Chen has left the group and so the team had to re-adjust the responsibilities. For starters, we will all work as team leaders and support each other on their respective roles. | Scheduled a weekly meeting considering various time zones and work schedules |  |  | 10 | 6 | 2 | 42.5 | 41 | 1.5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Mahim Choudhury | Overview,related works, non functional requrirements | Provided some execution plan |  |  | Present
Trevor Cardoza | Edit of Proposed High Level Requirments |  | Overview, (In Progress) System Architecture, Class Diagram
Delaney Sullivan | Wrote initial requirements
David Mulvihill | -Wrote the Management Plan including the Timeline Chart -Wrote the Configuration Management Plan | [6 empty] | -Set up the project repo including directory structure -Configured CI/CD and runners via GitHub Actions -Wrote Terraform code for IAC deployment to AWS

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Trevor Cardoza
Your Lead Roles: Backup Project Leader, Design and Implementation leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9.5 | 8.5 | 1 | 0 - learn git and flask, read several tutorials 1 - define high level requirements, 2 - figure out high level design and functionality, 5 - communicate about design implementation and get feed back 7 - research similar products, prepare presentation | 3 | 1 | 3 |  |  | 0.5 |  | 1 | 1. Edit SPPP and Presentation 2. Participate in Iteration 0 presentation | 1. Havent used Flask in awhile, getting up to speed | 1. Get up to speed and relook over past Flask Projects | 0 - continue to utilize Flask 1 - continue to define design 3 - Setup work enviroment and begin contributing to functionality | 8

## Mahim Choudhury
Your Lead Roles: Backup Project Leader, security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 17.5 | 16 | 1.5 | 0 - learn github and devops, read several tutorials 1 - define high-level security requirements, 5 - make project plan, set roles, schedule, lab-1 6 - set up github repo 7 - Research similar products, work on a presentation | 9 | 1 |  |  |  | 3 | 0.5 | 2.5 | 1. Wrote Overview, related works, and non-functional requirements of SPPP 2. Worked on the group summary tab for the progress report 3. Set up github and completed lab-1 4. Worked on and participated in Iteration 0 presentation | 1. Not too familiar with Flask, some devops and aws processes, security tools 2. Lost a team member which increased work share in a busy work-life schedule | 1. Continue to learn by online research and hopefully work on a simple flask app to get familiarized. COntinue to learn devops and aws processes and find out what sast tools can be simple to use. 2. Continue to collaborate with team members to take equal responsibilities and have each other's back | 0 - continue to learn Flask, nodejs 1 - Continue to define security requirements 2- Continue to learn devops processes, docker, aws, and sast tool 3 - Implement a basic hello world using reactjs and flask | 18

## David Mulvihill
Your Lead Roles: Configuration Managment Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 20.5 | 18 | 2.5 | 0 - learn GitHub actions 0 - learn Flask 3 - began local testing of Flask app on Docker 3 - began deploying infrastructure to AWS 5 - met with Team both through Zoom and communicated through Discord 5 - worked on Project documents 6 - set up and configured the GitHub repos 6 - began setting up AWS account for deployments 6 - began working on Dockerfile and for Flask app 6 - began writing Terraform for IAC deploments | 4 | 0 | 2 | 3 | 0 | 4 | 5 | 0 | 1. Set up and configured project repo. 2. Set up application directory structure. 3. Created Terraform files for deployment of infrastructure to AWS. 4. Began writing Terraform files for IAC deployment. 5. Began working on Dockerfile for deployment of the Flask app. 6. Began testing deployment of a sample containerized Flask app. | 1. No major issues at this point. 2. One minor issue relates to GitHub Actions and lack of maturity. 3. Another minor issue is the version of GitHub we are using, which is not Enterprise level and lacks some desired functionality. 4. Also, GitHub is not as good as GitLab. | - The identified issues are not one that can really be remedied. - The best approach at this time is to work within these limitations and as it becomes possible, search for and implement work-arounds. | 0 - continue learning Flask 3 - continue determing what infrastructure we will need 3 - continue looking for appropriate DevOps tools that faciliate the development and delivery of our application 6 - continue working on deploying/testing of infrastrucure and the containerized application | 14-20

## Delaney Sullivan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 8 | 7 | 1 | 0 - learned some AWS basic information and brushed up on Flask 1 - define high initial requirements, 5 - wrote risk management plan 6 - set up git 7 - prepare presentation | 2 | 1 | 2 |  |  | 0.5 | 1 | 0.5 | 1. Wrote initial program requirements 2. Wrote risk management plan 3. Added to presentation for iteration 0 | 1. Lost one team member, gained another 2. Figuring out communication cadence for the team | 1. catch new team member up 2. Currently working through best communication practices | 0 - continue to learn AWS as needed 1 - continue to define requirements 3 - assist with implementation as needed 5 - monitor risk mamangement plans | 9

## Zhe Huang
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 9 | 8 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1. Write QA sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | no | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0-write Unit test | 8