## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/05/23-09/12/23 | 1. Determined project, plan, roles 2. Made sure everyone understood the assignments and to-dos 3. The team had an initial understanding of what tools and processes the members need to learn 4. Wrote initial requirements 5. Wrote risk management plan | No technical issues to report | Hao Chen has left the group and so the team had to re-adjust the responsibilities. For starters, we will all work as team leaders and support each other on their respective roles. | Scheduled a weekly meeting considering various time zones and work schedules | n/a | n/a | 10 | 6 | 2 | 64.5 | 57.5 | 7 | 19 | 4 | 8 | 4 | 1 | 9 | 7.5
1 | 09/18/23-09/26/23 | 1. Update project plan, roles, requirements 2. Determine design patterns,architecture and to-dos 3. Team members continued to learn new topics 4. Wrote SDD documents 5. Prepared second presentation 6. Depoyment of infrastructure for the application is mostly complete. 7. The application is now deployed to the domain bumtelevision.com | No technical issues to report | - The only issue to report here is that our new team member, Jianing Li has not reported to the group. - We are assuming at this point that the studnet will not be joining the group. | We have schedule an additional meeting for midweek to ensure that we are staying on track with the project. | 14 | 20 | 7 | 6 | 1 | 71.75 | 62.75 | 9 | 16 | 3 | 8 | 12.5 | 4 | 5.75 | 12
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Mahim Choudhury | Overview,related works, non functional requrirements | Provided some execution plan | Introduction and security design |  | Present | -Wrote Authentication package -Wrote database package - Added the password hashing part in app.py
Trevor Cardoza | Edit of Proposed High Level Requirments |  | Overview, (In Progress) System Architecture, Class Diagram
Delaney Sullivan | Wrote initial requirements
David Mulvihill | -Wrote the Management Plan including the Timeline Chart -Wrote the Configuration Management Plan | We are using Jira to track our work, and I added/updated a number of stories I was working on. | I contributed the database design portion of the SDD |  | I participated in the presentation for Iteration_0 and Iteration_1 | I have contrituted the following: 1. Dockerfile 2. Docker Compose 3. Terraform IAC files 4. data base schema including relationships graphic |  | -Set up the project repo including directory structure -Configured CI/CD and runners via GitHub Actions -Wrote Terraform code for IAC deployment to AWS | I participated in meetings, took meeting mintues for meeting 3, and enaged with the Team on multiple occassions through our Discord channel.

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## TrevorCardoza
Your Lead Roles: Backup Project Leader, Design and Implementation leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9.5 | 8.5 | 1 | 0 - learn git and flask, read several tutorials 1 - define high level requirements, 2 - figure out high level design and functionality, 5 - communicate about design implementation and get feed back 7 - research similar products, prepare presentation | 3 | 1 | 3 |  |  | 0.5 |  | 1 | 1. Edit SPPP and Presentation | 1. Havent used Flask in awhile, getting up to speed | 1. Get up to speed and relook over past Flask Projects | 0 - continue to utilize Flask 1 - continue to define design 2 - Setup work enviroment and begin contributing to functionality | 8
2 | 05/11-05/24 | 7 | 6 | 1 | 1 - define high level requirements, 2 - figure out high level design of thw whole app and low level of login, 3 - get flask app running 7 - research similar products, prepare presentation | 0 | 1 | 2 | 2 |  | 0 |  | 1 | 1. Edit SDD and Presentation 2. Lead in Iteration 1 presentation |  | 1. Get up to speed and relook over past Flask Projects | 0 - continue to define design 2 - Get routing and functionality in Flask | 8

## MahimChoudhury
Your Lead Roles: Backup Project Leader, security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 17.5 | 16 | 1.5 | 0 - learn github and devops, read several tutorials 1 - define high-level security requirements, 5 - make project plan, set roles, schedule, lab-1 6 - set up github repo 7 - Research similar products, work on a presentation | 9 | 1 |  |  |  | 3 | 0.5 | 2.5 | 1. Wrote Overview, related works, and non-functional requirements of SPPP 2. Worked on the group summary tab for the progress report 3. Set up github and completed lab-1 4. Worked on and participated in Iteration 0 presentation | 1. Not too familiar with Flask, some devops and aws processes, security tools 2. Lost a team member which increased work share in a busy work-life schedule | 1. Continue to learn by online research and hopefully work on a simple flask app to get familiarized. COntinue to learn devops and aws processes and find out what sast tools can be simple to use. 2. Continue to collaborate with team members to take equal responsibilities and have each other's back | 0 - continue to learn Flask, nodejs 1 - Continue to define security requirements 2- Continue to learn devops processes, docker, aws, and sast tool 3 - Implement a basic hello world using reactjs and flask | 18
2 | 9/18-9/26 | 13.5 | 12 | 1.5 | 0 - learn design pattern, learn terraform 2 - set up security design 3 - implement password hashing | 4 |  | 4 | 4 |  |  |  |  | 1. Communicated and encouraged team mates to fullfill their responsibilites 2. Wrote the security design part of the SDD 3. Managed some Jira issues 4. Worked on password hashing | 1. Learning design pattern is a challange. Also I am new to terraform, I am trying to learn IAC quickly 2. Learned flask app by doing a hello-world app | 1. Learn from online and lectures. Terrform would be easier to learn by practice. | 0 - Continue learning design patterns, architecture, terraform 1 - Help the design team from security perspective 3. Start to work on implementing the app

## DavidMulvihill
Your Lead Roles: Configuration Managment Lead
Weeks # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/09 | 20.5 | 18 | 2.5 | 0 - learn GitHub actions 0 - learn Flask 3 - began local testing of Flask app on Docker 3 - began deploying infrastructure to AWS 5 - met with Team both through Zoom and communicated through Discord 5 - worked on Project documents 6 - set up and configured the GitHub repos 6 - began setting up AWS account for deployments 6 - began working on Dockerfile and for Flask app 6 - began writing Terraform for IAC deploments | 4 | 0 | 2 | 3 | 0 | 4 | 5 | 0 | 1. Set up and configured project repo. 2. Set up application directory structure. 3. Created Terraform files for deployment of infrastructure to AWS. 4. Began writing Terraform files for IAC deployment. 5. Began working on Dockerfile for deployment of the Flask app. 6. Began testing deployment of a sample containerized Flask app. | 1. No major issues at this point. 2. One minor issue relates to GitHub Actions and lack of maturity. 3. Another minor issue is the version of GitHub we are using, which is not Enterprise level and lacks some desired functionality. 4. Also, GitHub is not as good as GitLab. | - The identified issues are not one that can really be remedied. - The best approach at this time is to work within these limitations and as it becomes possible, search for and implement work-arounds. | 0 - continue learning Flask 3 - continue determing what infrastructure we will need 3 - continue looking for appropriate DevOps tools that faciliate the development and delivery of our application 6 - continue working on deploying/testing of infrastrucure and the containerized application | 14-20
2 - 3 | 09/12-09/23 | 27.75 | 25.25 | 2.5 | 1 - reviewed the RA to inform the RDS db schema 2 - worked on design of the db schema 3 - deployed infrastructure via TF and GitHub Actions; deployed the app on a container; 5 - assisted with presenations, participated in Team meetings, took the lead in submitting group iteration documents and creating releases in the project repo 6 - continued writing TF files for resource creation and configuration | 0 | 1 | 2 | 6.5 | 0 | 4.75 | 11 | 0 | 1. Continued working on organzing the repo including adding addtional directories for the app and database. 2. Continued creating Terraform files for deployment of infrastructure to AWS. 3. Continued IAC deployment via Terraform. 4. Finished working on Dockerfile for deployment of the Flask app. 5. Successfully deployed our containerized Flask app to ECS. 6. Worked on the application DB schema. 7. Updated the repo README.md file | - No major or minor issues to report. | - No issue status to report. | 1 - I will need to review the RA to inform the database schema design 2 - I will continue working on the database schema 3 - I will continue working on identifying AWS resources we will need for the application to function. 5 - I will continue working with the team through discord 6 - I need to continue deploying additional resources to AWS and also configure the ECS pipeline. | 15-30

## DelaneySullivan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 8 | 7 | 1 | 0 - learned some AWS basic information and brushed up on Flask 1 - define high initial requirements, 5 - wrote risk management plan 6 - set up git 7 - prepare presentation | 2 | 1 | 2 |  |  | 0.5 | 1 | 0.5 | 1. Wrote initial program requirements 2. Wrote risk management plan 3. Added to presentation for iteration 0 | 1. Lost one team member, gained another 2. Figuring out communication cadence for the team | 1. catch new team member up 2. Currently working through best communication practices | 0 - continue to learn AWS as needed 1 - continue to define requirements 3 - assist with implementation as needed 5 - monitor risk mamangement plans | 9
2 | 9/13-9/24 | 9.5 | 7.5 | 2 | 0 - reviewed the AWS we are using, brushed up on mySQL, learned some JavaScript 1 - added requirements 5 - updated risk management plan 6 - got access to AWS from David and poked around 7 - presentation meeting | 4 | 1 |  |  |  | 1 | 1 | 0.5 | 1. Added to requirements 2. Added to risk management plan 3. Helped with presentation video | 1. Minimal communciation from new team member | 1. Trying to contact them still | 0 - continue learning Javascript as needed 3 - help with mySQL as needed 5 - monitor risk management | 9

## ZheHuang
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 9 | 8 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1. Write QA sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | no | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0-write Unit test | 8
3 | 09/13-09/26 | 10 | 12 | 2 |  | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1. Write QA sections of SPPP 2. test code | no | 1. Keep on doing QA test | 0-Iteration test | 22