## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personnel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2022-10-05 | Redefine the project scope if necessary, and assign the tasks to other team members. | One person has dropped the class before assignment decided on, low risk. Another team member has dropped the class, however never had a role. No change | Closed
| Personal conflict with meeting times | Due to our time zone span, we could have trouble finding a meeting time for all | 3 | 4 | 3 | 18 | all team members | 2022-09-15 | Meeting minutes will be recorded for the person who is missing to review. They may ask questions as needed in the group discord | Group decided on one meeting time consistently per week. Added a second for the semester | Closed
| Team member added | Team member added to the team | 3 | 4 | 4 | 24 | all team members | 2023-10-10 | Provide team member with all notes to catch them up. Invite to all meetings | Unfortunately, we've had not much contact with our newest team member. They contributed to lab 1 however have not joined a meeting yet or notified us of conflict for missing it. They have since dropped and never contributed. No change to group | Closed
| Lack of motivation or responsibility | Team members not completing the tasks asked of them on time | 3 | 4 | 4 | 24 | all team members | 2022-09-15 | Set consistent expectations for team members that allow us time to group together to work something out before the deadline | We have set the due dates for our group internally earlier than is needed for the class to ensure we have ample time to address missing pieces together. All team members have met deadlines. | Closed
Communication | duplicate work | Two or more team members complete the same task without communication | 3 | 2 | 4 | 48 | all team members | 2023-10-10 | Make sure all work is outlined in the requirements and captured on the Jira board and assigned before work is started | During team meetings we have effectively assigned action items to reduce the possibility of this happening. We also have been using Jira to track what people are working on to add another layer of work documentation to reduce the possibility of duplicate work happening | Closed
| worked on wrong components | Someone works on the incorrect item | 2 | 3 | 4 | 48 | all team members | 2023-10-10 | During team meeting, clearly outline what needs to get done for the week and who is responsible. If something is missed, we have buffer time built in to finish | Our action items in our meeting minutes have guided what people are working on. This makes sure all work is assigned correctly for what needs to get done for this weel. If someone has wanted to pick up another task, they have been telling the team via discord to communicate completely | Closed
| useless work | work that is not required for the project | 2 | 3 | 4 | 48 | all team members | 2023-10-10 | Outline acceptance criteria to what is essential and communicate any extra work before beginning on it | All work is being discussed as a group before acted on to ensure that it is needed and helpful to our end product | Closed
Requirements | unclear requirements | Requriements are confusing and hard to understand or complete | 3 | 4 | 4 | 24 | requirement leader | 2023-09-26 | Have team members agree on the requirements in advance to ensure all understand what is being asked. Adjust only for clarity purposes | Agreed on final requirements as a team and what is feasible for us | closed
| scope creep | Additional work is being added to a task that was not its original intent | 4 | 4 | 3 | 12 | requirement leader | 2023-10-10 | Have minimal viable product actions and reach actions separated to ensure we are keeping tasks small and feasible. Can do reach actions as time permits | As items are being added, we've been focusing on MVP to ensure a functional product, rather than all extra items. Stories are being kept small to ensure completeness | closed
| constant requirements changes | Requirements are not staying consistent and are hard to follow | 2 | 4 | 3 | 24 | requirement leader | 2023-09-26 | Commit to requirements that complete the product, only add for missing pieces to the original goal, not a new goal | Kept our MVP requirements for a functional product, have reach requirements if able | Closed
Management | improper task assignments | Tasks are being assigned to the wrong people | 1 | 4 | 3 | 30 | team leader | 2023-09-26 | Confirm upon task assignment it is in the scope of that persons role, if a task is not assigned properly, immediate communication to quickly reassign to the proper team member | Collaborate with each other and share knowledge to help individuals to complete their tasks properly. Allow reassign of tasks if required. | Closed
| improper planning | Plan is not adequate to support the project completion and those working it | 3 | 4 | 4 | 24 | team leader | 2023-10-10 | Communicate holes in the plan and work with the members of the team to quickly change to plan to support us | Plan has us projected to complete our project efficently. | Closed
Technology competence | Not familiar with the framework used | One or more team members are unfamiliar with the framework being used | 3 | 3 | 2 | 18 | configuration leader | 2023-09-26 | Agreed upon a framework, for extra functionality read me's will be provided and group members more familiar with the framework will support those with less knowledge | Discussed moving to react however upon discussion, none of us had experience. Decided the stick with our original plan. At least one person has experience with all frameworks being used | Closed
| Not familiar with the programming language used | One or more team members are unfamiliar with the programming language being used | 2 | 4 | 2 | 16 | design and implementation leader | 2023-09-26 | Agreed upon a programming language, for extra functionality read me's will be provided and group members more familiar with the programming language will support those with less knowledge | Finalized programming languages, at least one if not more know all being used. Teaching as we go as needed | Closed
| Not familiar with unit testing | One or more team members are not familiar with unit testing | 2 | 2 | 2 | 32 | QA leader | 2023-09-26 | Agreed upon unit test usage, for extra functionality read me's will be provided and group members more familiar with the unit testing will support those with less knowledge | Whole team is aware of unit testing and the efforts needed to support the project | Closed
| Not familiar with Git | One or more team members are unfamiliar with Git | 2 | 4 | 2 | 16 | configuration leader | 2023-09-26 | Agreed upon a framework, for extra functionality read me's will be provided and group members more familiar with the framework will support those with less knowledge | David will provide more detailed process of the SCM and walk through them in the team meeting so no one is left in the dark and we all can learn | Closed
Design and implementation | Improper design | The design is not done properly for the project | 3 | 4 | 4 | 24 | design and implementation leader | 2023-10-10 | Create a complete design and immediately bring up any errors or missing pieces, pivot when needed | Design has been adjusted slightly to support project completetion on time | Closed
| improper technology stack | The technology stack does not support the project | 2 | 4 | 4 | 32 | configuration leader | 2022-09-15 | Utilize the proper tech stack and immediately bring up any errors or missing pieces, pivot when needed | Do research on what tech stack can be easily integrated with CICD and devops processes. | Closed
| Messy code | The code is hard to read and/or understand | 4 | 4 | 2 | 8 | QA leader | 2023-10-17 | Agree upon a coding standard and have group approval for code going into the main branch | Delaney went through an reorganized the code to ensure unity across all files | closed
Testing | Not enough testing | The project is not tested sufficiently | 3 | 4 | 4 | 24 | QA leader | 2023-10-17 | If bugs are found through usage without testing, then new tests will be added and code adjusted to fix them | Tests implemented in our code found minimal issues | Closed
Integration and deployment | Not enough time for integration and deployment | There is not enough time to fully integrate and deploy the project | 4 | 5 | 5 | 10 | design and implementation leader | 2023-10-10 | Set earlier dates to integrate and deploy aheadof schedule to build in buffer for error, and get any issues midigated | The application is now deployed to AWS and can be accessed via the domain http://bumtelevision.com/. | Closed
Security | not secure program | The program stores data in a not secure manor | 2 | 3 | 4 | 8 | security leader | 2023-10-17 | Confirm there is a security plan in place and add in more measures if it is found to be inadequate | The plan is to have the side communication secured with https, code security with a sast scanning tool, use secured user authentication, prevent sql injection | Closed